## Tracker (hidden)
SAPED Strategic Re-Branding
On Track | 0
3
Culture shift trigger | #N/A
Exposure/Footprint | #N/A
Strategy Fulfilment | #N/A
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Main Dashboard (hidden)
Serial | Strategy | Task Category | Tast | Responsibility | Status | Actual | Target | Frequency | Start Date | End Date | Duration | Sunburst
1 | Re-Branding | Strategy Fulfilment | Strategy Roll-out campaign | Re-branding team / People Strategy | Not Done | 0 | 1 | Yearly | 44197 | 44531 | 334 | 1
1 | Re-Branding | Culture shift trigger | Strategy Roll-out | Re-branding team / People Strategy | Not Done |  | TBD |  | 44287 | 44896 | 609 | 1
2 | Re-Branding | Culture shift trigger | Develop a slogan for the outreach program | Re-branding team / People Strategy | Not Done |  | Once |  | 44287 | 44317 | 30 | 1
3 | Re-Branding | Culture shift trigger | Outreach program for internally/external costumers (i.e celebrate local and international events, periodical accomplishment newsletter, strategy ordinated messages, and Re-brand Enlight ) | Re-branding team / People Strategy | Not Done |  | TBD |  | 44317 | 44531 | 214 | 1
4 | Re-Branding | Culture shift trigger | Synergize with “People” strategy to achieve “buy-in” thru the enhancement of workplace culture | Re-branding team / People Strategy | Not Done |  | 2 meetings per year |  | 44378 | 44531 | 153 | 1
5 | Re-Branding | Exposure/Footprint | Industry exposure (Number of SAPED SPE contribution) | Re-branding team / Publication team/ Awards team | Not Done |  | X% Incremental increase Abstracts & papers submissions/ year |  | 44378 | 44896 | 518 | 1
6 | Re-Branding | Exposure/Footprint | SAPED technical publications (Sandrose, JPT, oil & gas, world oil,…etc) | Re-branding team / Publication team/ Awards team | Not Done |  | 10 per year |  | NA | NA | NA | 1
7 | Re-Branding | Exposure/Footprint | Sponsorship of prestigious events (sponsor a technical OOK booth, one technical event in SAPED operational hubs, one non technical event) | Re-branding team / Publication team/ Awards team | Not Done |  | 3 Events per year |  | 44378 | 44531 | 153 | 1
9 | Re-Branding | Exposure/Footprint | Produce SAPED visual content (HSS&E, technical, OE, and promoting SAPED) | Re-branding team / Publication team/ Awards team | Not Done |  | 20 per year/ 4 per division |  | 44440 | 44621 | 181 | 1
10 | Re-Branding | Exposure/Footprint | Awards participating (external/internal) | Re-branding team / Publication team/ Awards team | Not Done |  | 5-10 participation per year |  | 44440 | 44531 | 91 | 1
11 | Re-Branding | Strategy Fulfilment | Strategy committee team formation and Dashboard creation | Re-branding team/ Strategy owners / SAPED Planning group | Not Done |  | Once |  | 44287 | 44593 | 306 | 1
12 | Re-Branding | Strategy Fulfilment | Budgeting and utilization of strategies' related resources | Re-branding team/ Strategy owners / SAPED Planning group | Not Done |  | 2 resource planning meeting/year |  | 44378 | 44531 | 153 | 1
13 | Re-Branding | Strategy Fulfilment | Meeting with strategy owners to measure (progress %) | Re-branding team/ Strategy owners / SAPED Planning group | Not Done |  | 4 meetings |  | 44440 | 44896 | 456 | 1
14.3333 | Digitalization | Automate Repetitive Tasks | Programs writing/ reports/ Approvals | SAPED iDM | Not Done |  | confirm whether tasks are those or the 41 tasks in slide 4 of the presentation!! |  |  |  |  | 1
15.4848 | Digitalization | Automate Repetitive Tasks | Data Entry | SAPED iDM | Not Done | [6 empty] | 1
16.6364 | Digitalization | To Analytics and Machine Learning | Creating Interactive Dashboards using Data Analytics Tools ( ex. ORION) | Yousef Mubarak Rami Abdulmohsen | Not Done | [6 empty] | 1
17.7879 | Digitalization | To Analytics and Machine Learning | Ensuring Adoption and Value | Yousef Mubarak Rami Abdulmohsen | Not Done | [6 empty] | 1
18.9394 | Digitalization | Capitalize on Corporate Systems | Joint projects with IT/ EXPEC ARC | SAPED iDM | Not Done | [6 empty] | 1
20.0909 | Digitalization | Capitalize on Corporate Systems | Joint projects with PEASD | SAPED iDM | Not Done | [6 empty] | 1
21.2424 | Digitalization | Remote Assistance | Invoice Jobs Remote witnessing | Mohammed Omran | Not Done | [6 empty] | 1
22.3939 | Digitalization | Remote Assistance | Smart headsets | Mohammed Omran | Not Done | [6 empty] | 1
23.5455 |  |  |  |  | Not Done | [6 empty] | 1
24.697 |  |  |  |  | Not Done | [6 empty] | 1
25.8485 |  |  |  |  | Not Done | [6 empty] | 1
27 |  |  |  |  | Not Done | [6 empty] | 1
28.1515 |  |  |  |  | Not Done | [6 empty] | 1
29.303 |  |  |  |  | Not Done | [6 empty] | 1
30.4545 |  |  |  |  | Not Done | [6 empty] | 1
31.6061 |  |  |  |  | Not Done | [6 empty] | 1
32.7576 |  |  |  |  | Not Done | [6 empty] | 1
33.9091 |  |  |  |  | Not Done | [6 empty] | 1
35.0606 |  |  |  |  | Not Done | [6 empty] | 1
36.2121 |  |  |  |  | Not Done | [6 empty] | 1
37.3636 |  |  |  |  | Not Done | [6 empty] | 1
38.5152 |  |  |  |  | Not Done | [6 empty] | 1
39.6667 |  |  |  |  | Not Done | [6 empty] | 1
40.8182 |  |  |  |  | Not Done | [6 empty] | 1
41.9697 |  |  |  |  | Not Done | [6 empty] | 1
43.1212 |  |  |  |  | Not Done | [6 empty] | 1
44.2727 |  |  |  |  | Not Done | [6 empty] | 1
45.4242 |  |  |  |  | Not Done | [6 empty] | 1
46.5758 |  |  |  |  | Not Done | [6 empty] | 1

## Main Dashboard (2) (hidden)
[9 empty] | For regular action items; this should remain "once", for KPIs; frequency should be selected accordingly. | KPI/action item Actual vs ETC |  |  |  | Status based on whether action item/KPI data have been cmopleted
# | Strategy | Sub-Strategy | Initiative | Type: Action Item / KPI | Action Item | Responsibility | KPT Actual | KPI Target | Frequency | Start Date | Expected Completion Date (ETC) | Actual Completion Date | Completion % (100 or current progress % if not completed) | Completion Status (Completed/ Not Completed) | Due/Not Due | Compliance (within ETC vs beyond ETC) | Duration
1 | Re-Branding | Strategy Fulfilment | Strategy committee team formation and Dashboard creation | Action Item | Charter development | Nahr |  |  |  | 2021-06-10 | 2021-11-25 |  | 75% | Not Completed | Due | Beyond ETC | 168 | updated on 6/20, removed "Not due yet" and replaced it with "within ETC" to have a more clear visulaization on Spotfire | Beyond ETC
2 | Re-Branding | Strategy Fulfilment | Strategy committee team formation and Dashboard creation | Action Item | Tracking Dashboard | Ibrahim |  |  |  | 2021-05-07 | 2021-10-30 |  | 90% | Not Completed | Due | Beyond ETC | 176
3 | Re-Branding | Strategy Fulfilment | Budgeting and utilization of strategies' related resources. | Action Item | Budget communication with manager group | Nahr |  |  |  | 2021-06-08 | 2021-06-21 |  | 100% | Completed | Due | Beyond ETC | 13
4 | Re-Branding | Strategy Fulfilment | Meeting with strategy champions to track % progress | Action Item | Meeting in 3rd quarter | Nahr - Atwi |  |  |  | 2021-06-10 | 2021-07-29 |  | 100% | Completed | Due | Beyond ETC | 49
5 | Re-Branding | Culture Shift Trigger | Develop SAPED Brand Identity System (SBIS) “Diversity and legacy” | Action Item | Complete SBIS | Nahr - Atwi - Alatigue |  |  |  | 2021-06-17 | 2021-10-30 |  | 70% | Not Completed | Due | Beyond ETC | 135
6 | Re-Branding | Culture Shift Trigger | Strategy Roll-out | Action Item | After completing SBIS | Nahr - Atwi - Alatigue |  |  |  | 2021-08-01 | 2021-11-30 |  | 40% | Not Completed | Due | Beyond ETC | 121
7 | Re-Branding | Culture Shift Trigger | Outreach program for internally/external costumers (i.e celebrate local and international events, and periodical accomplishment newsletter) | Action Item | Outreaching schools and planning events | Alatigue - Abdulrahman Almulhim - Aljughaiman |  |  |  | 2021-08-15 | 2021-09-30 |  | 75% | Not Completed | Due | Beyond ETC | 46
8 | Re-Branding | Culture Shift Trigger | Synergize with “People” strategy to achieve “buy-in” thru the enhancement of workplace culture | Action Item | Collaborate with people for applying culture shift | Nahr - Meshakhes - Abdulaziz Sultan |  |  |  | 2021-06-01 | 2021-12-30 |  | 50% | Not Completed | Due | Beyond ETC | 212
9 | Re-Branding | Exposure/Footprint | Produce SAPED visual content (HSS&E, technical, OE, and promoting SAPED) | Action Item | Budget allocation for the visual material is requested | Shaima | [6 empty] | 100% | Completed | Due | Beyond ETC | 0
10 | Re-Branding | Exposure/Footprint | Produce SAPED visual content (HSS&E, technical, OE, and promoting SAPED) | Action Item | Established contact with the Media production division | Shaima | [6 empty] | 100% | Not Completed | Due | Beyond ETC | 0
11 | Re-Branding | Exposure/Footprint | Awards participating (external/internal) | Action Item | Align with the award committee to publicize achievement | Abdullah Alghamdi | [6 empty] | 50% | Not Completed | Due | Beyond ETC | 0
12 | Re-Branding | Exposure/Footprint | Industry exposure program (Public relation with stakeholders) | Action Item | Outline a plan to enhance public relations with industry stakeholders (Saudi ARAMCO, SPE, SC, universities, IOC/NOC,…etc) | Alatigue - Abdulrahman Almulhim - Aljughaiman | [6 empty] | 50% | Not Completed | Due | Beyond ETC | 0
13 | Re-Branding | Exposure/Footprint | SAPED technical publications (Sandrose, JPT, oil & gas, world oil,…etc) | Action Item | Already established communication with SPE publication (Sand Rose) | Alatigue - Abdulrahman Almulhim - Aljughaiman | [6 empty] | 70% | Not Completed | Due | Beyond ETC | 0
14 | Re-Branding | Exposure/Footprint | SAPED technical publications (Sandrose, JPT, oil & gas, world oil,…etc) | Action Item | Develop vocal communication point | Abdulrahman Almulhim | [6 empty] | 100% | Completed | Due | Beyond ETC | 0
15 | Re-Branding | Exposure/Footprint | SAPED technical publications (Sandrose, JPT, oil & gas, world oil,…etc) | Action Item | Media and Newsletter Publication Review (MNPR) Committee | Abdulaziz Sultan | [6 empty] | 30% | Not Completed | Due | Beyond ETC | 0
16 | Re-Branding | Exposure/Footprint | Participation and in prestigious events (represent SAPED in technical OOK booth, technical events in SAPED operational hubs, social events) | Action Item | Budget requested & outline the details of the event | Nahr - Abdulaziz Sultan | [6 empty] | 85% | Not Completed | Due | Beyond ETC | 0
17 | Cost Efficiency | Value Creation | GOSP & Equipment Optimization | Action Item | Enrgey conservation while meeting production target | Optimization team |  |  |  | 2021-08-01 | Continuous |  | 100% | Not Completed | Note Due | Within ETC
18 | Cost Efficiency | Value Creation | WO Optimization | Action Item | Utilize 1 available solution/introduce 1 new solution to avoid rig operation per year per division | All divisions |  |  |  | 2021-10-01 | Continuous |  | 100% | Not Completed | Note Due | Within ETC
19 | Cost Efficiency | Value Creation | Invoice/Non-invoice Optimization | Action Item | Introduce 1 standardized procedure among SAPED divisions in Well-IP | Digitalization Team |  |  |  | 2022-01-01 | Continuous |  | 100% | Not Completed | Note Due | Within ETC
20 | Cost Efficiency | Value Creation | Invoice/Non-invoice Optimization | Action Item | U-Wise revision by end Q-1 2022 | U-Wise Manual Team |  |  |  | 2022-01-01 | 2022-03-31 |  | 100% | Not Completed | Due | Beyond ETC | 89
21 | Cost Efficiency | Cost Intelligence Hub | Data analysis & modeling | Action Item | Reduce well integrity requirements by 5% annually | U-Wise Manual Team |  |  |  | 2022-04-01 | Continuous |  | 100% | Not Completed |  | Within ETC
22 | Cost Efficiency | Cost Intelligence Hub | Data analysis & modeling | Action Item | Build all SAPED well models | All PipeSim trained Pes |  |  |  | 2021-08-01 | 2022-06-30 |  | 100% | Not Completed |  | Beyond ETC | 333
23 | Cost Efficiency | Culture Creation | PMP Goal | Action Item | One Goal per employees to participate in at least 1 CE Initiative | SAPED P&P |  |  |  | 2021-09-01 | Continuous |  | 100% | Not Completed |  | Within ETC
24 | Cost Efficiency | Culture Creation | Success Stories | Action Item | Build SAPED CE dashboard | Digitalization Team |  |  |  | 2022-01-01 | 2022-12-31 |  | 100% | Not Completed |  | Beyond ETC | 364
25 | Cost Efficiency | Culture Creation | Success Stories | Action Item | Share 2 success stories per division per year in an annual SAPED workshop/event | All divisions |  |  |  | 2022-01-01 | Continuous |  | 100% | Not Completed |  | Within ETC
26 | Cost Efficiency | Culture Creation | Employee Awards | Action Item | Award 1 employees per division per year | All divisions |  |  |  | 2022-01-01 | Continuous |  | 100% | Not Completed |  | Within ETC
27 | Cost Efficiency | Culture Creation | Employee Awards | Action Item | Nominate/recognize 1 employee in awards outside SAPED | All divisions |  |  |  | 2022-01-01 |  |  | 100% | Not Completed |  | Beyond ETC | -44562
28 | Sustainability | Environmental Technologies and Solutions | Innovative PE (Ball Sealers) | Action Item | Study the feasibility of Ball Sealers implementation in SAPED | GGPED - Moataz Harbi |  |  |  | Q4 2021 | Q2 2022 |  | 0% | Not Completed |  | Within ETC
29 | Sustainability | Environmental Technologies and Solutions | Innovative PE (Ball Sealers) | Action Item | Evaluating the market for the technology provider | GGPED - Moataz Harbi |  |  |  | Q2 2022 | Q3 2022 |  | 0% | Not Completed |  | Within ETC
30 | Sustainability | Environmental Technologies and Solutions | Innovative PE (Ball Sealers) | Action Item | Establish an economical & enviromental review for ball sealers | GGPED - Moataz Harbi |  |  |  | Q3 2022 | Q4 2022 |  | 0% | Not Completed |  | Within ETC
31 | Sustainability | Environmental Technologies and Solutions | Innovative PE (Ball Sealers) | KPI | Initiate and complete TTR & MOC (If Required) | GGPED - Moataz Harbi |  | 100 |  | Q1 2023 | Q4 2023 |  | 0% | Not Completed |  | Within ETC
32 | Sustainability | Environmental Technologies and Solutions | Innovative PE (Ball Sealers) | Action Item | Magnitude tracking of groundwater conservation | GGPED - Moataz Harbi |  |  |  | Q1 2023 | Q4 2023 |  | 0% | Not Completed |  | Within ETC
33 | Sustainability | Environmental Technologies and Solutions | Innovative PE (ML Frac Design) | Action Item | Compile all raw pre-frac data and post-frac data | GGPED - Moataz Harbi |  |  |  | Q4 2021 | Q2 2022 |  | 0% | Not Completed |  | Within ETC
34 | Sustainability | Environmental Technologies and Solutions | Innovative PE (ML Frac Design) | Action Item | Design a machine learning algorithm to read the frac data and recommend frac design | GGPED - Moataz Harbi |  |  |  | Q2 2022 | Q3 2023 |  | 0% | Not Completed |  | Within ETC
35 | Sustainability | Environmental Technologies and Solutions | Innovative PE (ML Frac Design) | Action Item | Continuous enhancement of ML algorithm to conserve the integrity of the well | GGPED - Moataz Harbi |  |  |  | Q3 2023 | Q4 2023 |  | 0% | Not Completed |  | Within ETC
36 | Sustainability | Environmental Technologies and Solutions | Innovative PE (Improved Chemistry for Frac Jobs) | KPI | Expand the collaboration with in-house and in-Kingdom entities to identifiy for chemical solutions | GGPED - Moataz Harbi |  | 100 |  | Q4 2021 | Q2 2022 |  | 0% | Not Completed |  | Within ETC
37 | Sustainability | Environmental Technologies and Solutions | Innovative PE (Improved Chemistry for Frac Jobs) | KPI | Construct workshops to devolop in-Kingdom fit-for-purpose frac fluid | GGPED - Moataz Harbi |  | 5 |  | Q4 2021 | Q2 2022 |  | 0% | Not Completed |  | Within ETC
38 | Sustainability | Environmental Technologies and Solutions | Innovative PE (Improved Chemistry for Frac Jobs) | Action Item | Study the feasibility of newly purposed frac fluids enviromentaly & economically | GGPED - Moataz Harbi |  |  |  | Q2 2022 | Q1 2023 |  | 0% | Not Completed |  | Within ETC
39 | Sustainability | Environmental Technologies and Solutions | Innovative PE (Energized Frac Operations) | Action Item | Explore CO2 in-Kingdom providers | GGPED - Hamad Kulaib |  |  |  | Q1 2022 | Q3 2022 |  | 0% | Not Completed |  | Within ETC
40 | Sustainability | Environmental Technologies and Solutions | Innovative PE (Energized Frac Operations) | Action Item | Study the practicality and direct enviromental impact of CO2 fracking | GGPED - Hamad Kulaib |  |  |  | Q1 2022 | Q3 2022 |  | 0% | Not Completed |  | Within ETC
41 | Sustainability | Environmental Technologies and Solutions | Innovative PE (Energized Frac Operations) | KPI | Initiate and complete TTR & MOC for CO2 fracking (If Required) | GGPED - Hamad Kulaib |  | 100 |  | Q3 2022 | Q2 2023 |  | 0% | Not Completed |  | Within ETC
42 | Sustainability | Environmental Technologies and Solutions | Innovative PE (Improved Chemistry for Frac Jobs) | Action Item | Initiate and complete TTR & MOC (If Required) | GGPED - Moataz Harbi |  |  |  | Q1 2023 | Q4 2023 |  | 0% | Not Completed |  | Within ETC
43 | Sustainability | Environmental Technologies and Solutions | Innovative PE (Seawater for CT Operations) | Action Item | Evaluate the utilization Sea water in CT operations | GGPED- Sultan Attiah |  |  |  | Q4 2021 | Q2 2022 |  | 0% | Not Completed |  | Within ETC
44 | Sustainability | Environmental Technologies and Solutions | Innovative PE (Seawater for CT Operations) | KPI | Magnitude tracking of groundwater conservation | GGPED- Sultan Attiah |  | 100 |  | Q2 2022 | Q1 2023 |  | 0% | Not Completed |  | Within ETC
45 | Sustainability | Environmental Technologies and Solutions | Green PE (Ground water conservation) | Action Item | Evaluate the practicality and environmental impact of various desalination methods (cost , Co2, logistics) &Compare the carbon footprint of desalination vs. ground water operations | GGPED - Abdullah Ghamdi & SGPED - Surajit Halder |  |  |  | Q2 2022 | Q4 2022 |  | 0% | Not Completed |  | Within ETC
46 | Sustainability | Environmental Technologies and Solutions | Green PE (Ground water conservation) | Action Item | Magnitude tracking of groundwater conservation | GGPED - Abdullah Ghamdi & SGPED - Surajit Halder |  |  |  | Q1 2023 | Q4 2023 |  | 0% | Not Completed |  | Within ETC
47 | Sustainability | Environmental Technologies and Solutions | Green PE (Zero Flaring - RTP & Closed loop FB) | Action Item | Evaluating the market for the technology provider | GGPED - Abdullah Ghamdi & SGPED - Surajit Halder |  |  |  | Q2 2021 | Q2 2022 |  | 0% | Not Completed |  | Within ETC
48 | Sustainability | Environmental Technologies and Solutions | Green PE (Zero Flaring - RTP & Closed loop FB) | Action Item | Study the CO2 & SO2 footprint of flaring vs. closed-loop system | GGPED - Abdullah Ghamdi & SGPED - Surajit Halder |  |  |  | Q2 2022 | Q3 2022 |  | 0% | Not Completed |  | Within ETC
49 | Sustainability | Environmental Technologies and Solutions | Green PE (Zero Flaring - RTP & Closed loop FB) | Action Item | Initiate and complete TTR & MOC (If Required) | GGPED - Abdullah Ghamdi & SGPED - Surajit Halder |  |  |  | Q3 2021 | Q1 2023 |  | 0% | Not Completed |  | Within ETC
50 | Sustainability | Environmental Technologies and Solutions | Green PE (Zero Flaring - RTP & Closed loop FB) | KPI | Evaluate the market providers for closed-loop system | GGPED - Abdullah Ghamdi & SGPED - Surajit Halder |  | 100 |  | Q2 2022 | Q3 2022 |  | 0% | Not Completed |  | Within ETC
51 | Sustainability | Environmental Technologies and Solutions | Green PE (Zero Flaring - RTP & Closed loop FB) | Action Item | Build a model of current production network that also suggest (RTP) whenever viable | GGPED - Abdullah Ghamdi & SGPED - Surajit Halder |  |  |  | Q4 2021 | Q2 2022 |  | 0% | Not Completed |  | Within ETC
52 | Sustainability | Environmental Technologies and Solutions | Green PE (Zero Flaring - RTP & Closed loop FB) | Action Item | Formulate criteria for suggesting candidates of closed-loop operations | GGPED - Abdullah Ghamdi & SGPED - Surajit Halder |  |  |  | Q2 2022 | Q3 2022 |  | 0% | Not Completed |  | Within ETC
53 | Sustainability | Environmental Technologies and Solutions | Green PE (Zero Flaring - RTP & Closed loop FB) | Action Item | Nominate candidates for closed-loop system operations | GGPED - Abdullah Ghamdi & SGPED - Surajit Halder |  |  |  | Q3 2022 | Q4 2022 |  | 0% | Not Completed |  | Within ETC
54 | Sustainability | Environmental Technologies and Solutions | Green PE (Zero Flaring - RTP & Closed loop FB) | Action Item | Magnitude tracking of gas flaring avoidance | GGPED - Abdullah Ghamdi & SGPED - Surajit Halder |  |  |  | Q1 2023 | Q2 2023 |  | 0% | Not Completed |  | Within ETC
55 | Sustainability | Environmental Technologies and Solutions | Green PE (Clamp-on Metering) | KPI | Evaluating the market for the technology provider | SGPED - Ibrahim Zefzafy |  | 100 |  | Q4 2021 | Q2 2022 |  | 0% | Not Completed |  | Within ETC
56 | Sustainability | Environmental Technologies and Solutions | Green PE (Clamp-on Metering) | Action Item | Study feasability & the reliability of alternative technologies to eliminate dismantling work | SGPED - Ibrahim Zefzafy |  |  |  | Q4 2021 | Q4 2022 |  | 0% | Not Completed |  | Within ETC
57 | Sustainability | Environmental Technologies and Solutions | Green PE (Clamp-on Metering) | Action Item | Initiate and complete TTR & MOC (If Required) | SGPED - Ibrahim Zefzafy |  |  |  | Q1 2023 | Q3 2023 |  | 0% | Not Completed |  | Within ETC
58 | Sustainability | Environmental Technologies and Solutions | Green PE (Clamp-on Metering) | Action Item | Magnitude tracking of clamp-on metering cost saving/avoidance. | SGPED - Ibrahim Zefzafy |  |  |  | Q1 2023 | Q4 2023 |  | 0% | Not Completed |  | Within ETC
59 | Sustainability | Environmental Technologies and Solutions | Green PE (Mobile Wellhead Gas Compression ) | Action Item | Initiate and complete TTR & MOC (If Required) | RFGPED - Muhammad Idris |  |  |  | Q2 2021 | Q1 2022 |  | 0% | Not Completed |  | Within ETC
60 | Sustainability | Environmental Technologies and Solutions | Green PE (Mobile Wellhead Gas Compression ) | KPI | Introduce technology as standard | RFGPED - Muhammad Idris |  | 100 |  | Q3 2021 | Q2 2022 |  | 0% | Not Completed |  | Within ETC
61 | Sustainability | Environmental Technologies and Solutions | Green PE (Mobile Wellhead Gas Compression ) | Action Item | Magnitude tracking of gas flaring avoidance | RFGPED - Muhammad Idris |  |  |  | Q1 2023 | Q3 2023 |  | 0% | Not Completed |  | Within ETC
62 | Sustainability | Health, Safety, & Security | Wellness Program | Action Item | Identify the required resourses (Budgeting) | HSSE Leader & SAPED HR Advisor |  |  |  | Q2 2021 | Q4 2021 |  | 0% | Not Completed |  | Within ETC
63 | Sustainability | Health, Safety, & Security | Wellness Program | Action Item | Establish baseline employee wellness | HSSE Leader & SAPED HR Advisor |  |  |  | Q3 2021 | Q2 2022 |  | 0% | Not Completed |  | Within ETC
64 | Sustainability | Health, Safety, & Security | Wellness Program | Action Item | Build a taskforce that is responsible for promoting health & wellness of employees | HSSE Leader & SAPED HR Advisor |  |  |  | Q4 2021 | Q2 2022 |  | 0% | Not Completed |  | Within ETC
65 | Sustainability | Health, Safety, & Security | Wellness Program | KPI | Distribute monthly/quarterly wellness articles published by wellness taskforce | HSSE Leader & SAPED HR Advisor & wellness taskforce |  | 100 |  | Q4 2021 | Q1 2022 |  | 0% | Not Completed |  | Within ETC
66 | Sustainability | Health, Safety, & Security | Wellness Program | KPI | Evaluate the logistics and feasibility addition of onsite mini fitness center | HSSE Leader & SAPED HR Advisor & wellness taskforce |  | 100 |  | Q4 2021 | Q1 2022 |  | 0% | Not Completed |  | Within ETC
67 | Sustainability | Health, Safety, & Security | Wellness Program | Action Item | propose and faciliate department level wellness events | HSSE Leader & SAPED HR Advisor & wellness taskforce |  |  |  | Q3 2021 | Q1 2022 |  | 0% | Not Completed |  | Within ETC
68 | Sustainability | Agility & Resilience | Orion 4.0 | Action Item | Identify all related databases to ensure the functionality of ORION 4.0 | SAPED DM & iScope Supervisor |  |  |  | Q4 2021 | Q2 2022 |  | 0% | Not Completed |  | Within ETC
69 | Sustainability | Agility & Resilience | Orion 4.0 | Action Item | Automate the daily functions of PE to maximize efficiency | SAPED DM & iScope Supervisor |  |  |  | Q2 2022 | Q4 2022 |  | 0% | Not Completed |  | Within ETC
70 | Sustainability | Agility & Resilience | Orion 4.0 | KPI | Complete deployment of first phase of PE ORION 4.0 | SAPED DM & iScope Supervisor |  | 100 |  | Q4 2022 | Q1 2023 |  | 0% | Not Completed |  | Within ETC
71 | Sustainability | Agility & Resilience | Program Automation (Well-IP) | Action Item | Scope - Completed | SAPED DM & iScope Supervisor |  |  |  | Q1 2021 | Q2 2021 |  | 100% | Not Completed |  | Within ETC
72 | Sustainability | Agility & Resilience | Program Automation (Well-IP) | Action Item | Development - Completed | SAPED DM & iScope Supervisor |  |  |  | Q2 2021 | Q3 2021 |  | 0% | Not Completed |  | Within ETC
73 | Sustainability | Agility & Resilience | Program Automation (Well-IP) | Action Item | Deployment - Completed | SAPED DM & iScope Supervisor |  |  |  | Q2 2021 | Q3 2021 |  | 0% | Not Completed |  | Within ETC
74 | Sustainability | Agility & Resilience | Program Automation (Well-IP) | KPI | Continous Enhancement of WELL IP system by improving the generation process and approval workflow of invoice programs - ongoing | SAPED DM & iScope Supervisor |  | 100 |  | Q3 2021 | Q4 2021 |  | 0% | Not Completed |  | Within ETC
75 | Sustainability | Agility & Resilience | Program Automation (Well-IP) | KPI | Introduce generation of multi-well request in WELL IP | SAPED DM & iScope Supervisor |  | 1 |  | Q4 2021 | Q1 2022 |  | 0% | Not Completed |  | Within ETC
76 | Sustainability | Agility & Resilience | PE AI Advisor | Action Item | Assess the scope of the project | Sanjiv Kumar & Ramiro Cedeno |  |  |  | Q4 2021 | Q1 2022 |  | 0% | Not Completed |  | Within ETC
77 | Sustainability | Agility & Resilience | PE AI Advisor | Action Item | Generate a method to categorize SAPED archived files | Sanjiv Kumar & Ramiro Cedeno |  |  |  | Q1 2022 | Q3 2022 |  | 0% | Not Completed |  | Within ETC
78 | Sustainability | Agility & Resilience | PE AI Advisor | Action Item | Build search engine that provide all relevant data in PE advisor | Sanjiv Kumar & Ramiro Cedeno |  |  |  | Q3 2022 | Q2 2023 |  | 0% | Not Completed |  | Within ETC
79 | Sustainability | Agility & Resilience | PE AI Advisor | Action Item | Deployment | Sanjiv Kumar & Ramiro Cedeno |  |  |  | Q2 2023 | Q4 2023 |  | 0% | Not Completed |  | Within ETC
80 | Sustainability | Agility & Resilience | Enhance TTR Workflow | KPI | Assess the scope of the project | Simeon Bolarinwa & SAPED DM & iScope Supervisor |  | 100 |  | Q4 2021 | Q2 2022 |  | 0% | Not Completed |  | Within ETC
81 | Sustainability | Agility & Resilience | Enhance TTR Workflow | Action Item | Improve the technology trial testing system and expedite the qualification process | Simeon Bolarinwa & SAPED DM & iScope Supervisor |  |  |  | Q2 2022 | Q4 2022 |  | 0% | Not Completed |  | Within ETC
82 | Sustainability | Agility & Resilience | Enhance TTR Workflow | Action Item | Deploy and Issue a standardize implementation report to ensure the execution of qualified technology in the fields | Simeon Bolarinwa & SAPED DM & iScope Supervisor |  |  |  | Q4 2022 | Q2 2023 |  | 0% | Not Completed |  | Within ETC
83 | Sustainability | Production Sustainability | Production Engineering Advisory & Compliance Environment (PEACE) | Action Item | Asses Scope of the Project | SAPED DM & iScope Supervisor |  |  |  | Q4 2021 | Q2 2022 |  | 0% | Not Completed |  | Within ETC
84 | Sustainability | Production Sustainability | Production Engineering Advisory & Compliance Environment (PEACE) | KPI | Confirm the accuracy and availability of needed data to be assimilated in the system | SAPED DM & iScope Supervisor |  | 100 |  | Q2 2022 | Q3 2022 |  | 0% | Not Completed |  | Within ETC
85 | Sustainability | Production Sustainability | Production Engineering Advisory & Compliance Environment (PEACE) | Action Item | Construct intelligent models for existing wells and pipelines | SAPED DM & iScope Supervisor |  |  |  | Q3 2022 | Q4 2022 |  | 0% | Not Completed |  | Within ETC
86 | Sustainability | Production Sustainability | Production Engineering Advisory & Compliance Environment (PEACE) | Action Item | Integrate AI/ML to utilize models for analysis and diagnostic and recommend remedial work | SAPED DM & iScope Supervisor |  |  |  | Q4 2022 | Q2 2023 |  | 0% | Not Completed |  | Within ETC
87 | Sustainability | Production Sustainability | Production Engineering Advisory & Compliance Environment (PEACE) | Action Item | Set designed workflows for AI to perform diagnostic well integrity jobs (predictions) | SAPED DM & iScope Supervisor |  |  |  | Q2 2023 | Q3 2023 |  | 0% | Not Completed |  | Within ETC
88 | Sustainability | Production Sustainability | Production Engineering Advisory & Compliance Environment (PEACE) | KPI | Deployment and continous improvement | SAPED DM & iScope Supervisor |  | 100 |  | Q3 2023 | Q4 2023 |  | 0% | Not Completed |  | Within ETC
89 | Sustainability | Production Sustainability | Network Optimizer | Action Item | Assess Scope of the project | Mazen Modahi & Muhammad Hajri |  |  |  | Q4 2021 | Q1 2022 |  | 0% | Not Completed |  | Within ETC
90 | Sustainability | Production Sustainability | Network Optimizer | Action Item | Identify existing oil/gas transfer lines between GOSP’s and gas plants to optimize operations and reduce operating constraints | Mazen Modahi & Muhammad Hajri |  |  |  | Q1 2022 | Q2 2022 |  | 0% | Not Completed |  | Within ETC
91 | Sustainability | Production Sustainability | Network Optimizer | Action Item | Build Prosper/Gap or PIPESIM modeling dashboard for all SAOO fields network to model production and injection network. That can Identify maximum potential capacity and operating limitation. | Mazen Modahi & Muhammad Hajri |  |  |  | Q2 2022 | Q1 2023 |  | 0% | Not Completed |  | Within ETC
92 | Sustainability | Production Sustainability | Network Optimizer | Action Item | Magnitude tracking of network productivity enhancements cases from application | Mazen Modahi & Muhammad Hajri |  |  |  | Q1 2023 | Q2 2023 |  | 0% | Not Completed |  | Within ETC
93 | Sustainability | Production Sustainability | Network Optimizer | KPI | Evaluate all transfer capacity and update transfer capacity potential | Mazen Modahi & Muhammad Hajri |  | 100 |  | Q2 2023 | Q3 2023 |  | 0% | Not Completed |  | Within ETC
94 | Sustainability | Production Sustainability | Network Optimizer | Action Item | Deployment and continous updates to network | Mazen Modahi & Muhammad Hajri |  |  |  | Q3 2023 | Q4 2023 |  | 0% | Not Completed |  | Within ETC
95 | Sustainability | Production Sustainability | PE Mobile App | Action Item | Assess the scope of the project and confirm the proposed functions | Abdullah Ghamdi & SAPED DM & iScope suprevisor |  |  |  | Q4 2021 | Q1 2022 |  | 0% | Not Completed |  | Within ETC
96 | Sustainability | Production Sustainability | PE Mobile App | Action Item | Establish a secure data pathway to the current database or build secure cloud to upload programs & manuals into and launch app | Abdullah Ghamdi & SAPED DM & iScope suprevisor |  |  |  | Q1 2022 | Q3 2022 |  | 0% | Not Completed |  | Within ETC
97 | Sustainability | Production Sustainability | PE Mobile App | Action Item | Design a KMW calculator as a part of PE mobile app | Abdullah Ghamdi & SAPED DM & iScope suprevisor |  |  |  | Q3 2022 | Q4 2022 |  | 0% | Not Completed |  | Within ETC
98 | Sustainability | Production Sustainability | PE Mobile App | Action Item | Upload OIM’S Manuals and SOP’s into the app | Abdullah Ghamdi & SAPED DM & iScope suprevisor |  |  |  | Q3 2022 | Q4 2022 |  | 0% | Not Completed |  | Within ETC
99 | Sustainability | Production Sustainability | PE Mobile App | KPI | Automate dublicating issued programs (well IP & conventual programs) into the secured cloud | Abdullah Ghamdi & SAPED DM & iScope suprevisor |  | 100 |  | Q4 2022 | Q1 2023 |  | 0% | Not Completed |  | Within ETC
100 | Digitization | x | x | Action Item | x | x | [6 empty] | 0% | Not Completed |  | Beyond ETC | 0
101 | People development and Engagment | Performance & Wellbeing | Engagment communication | Action Item | Coordinate SAPED manager workshop with SAPED supervisors | Abdulaziz Shieban |  |  |  | Q4 2021 | Q4 2021 |  | 0% | Not Completed |  | Within ETC
102 | People development and Engagment | Performance & Wellbeing | Engagment communication | Action Item | Launch the employee voice channel | Abdulaziz Shieban |  |  |  |  | Q4 2021 |  |  | Not Completed |  | Within ETC
103 | People development and Engagment | Performance & Wellbeing | People Engagment Survey | Action Item | Launch SAPED internal survey (in Arabic and English) | Abdulrahman Mishkhes & Abdulaziz Shieban |  |  |  |  | Q4 2022 |  |  | Not Completed |  | Within ETC
104 | People development and Engagment | T&D Administration & Oversigh | SAPED development program | Action Item | Develop IDP Dashboard | SPEED Team |  |  |  | Q3 2021 | Q4 2022 |  |  | Not Completed |  | Within ETC
105 | People development and Engagment | T&D Administration & Oversigh | SAPED development program | Action Item | Assess & Benchmark developmental program | SPEED Team |  |  |  | Q3 2021 | Q4 2022 |  |  | Not Completed |  | Within ETC
106 | People development and Engagment | T&D Administration & Oversigh | SAPED development program | Action Item | Prepare Development program upgrade proposal | Abdulrahman Mishkhes |  |  |  | Q3 2021 | Q4 2021 | completed |  | Not Completed |  | Within ETC
107 | People development and Engagment | Performance & Wellbeing | Engagment communication | Action Item | Select engagement ambassadors (Divisions and unit level) | SAPED PD&E team |  |  |  | Q3 2021 | Q4 2021 |  |  | Not Completed |  | Within ETC
108 | People development and Engagment | Performance & Wellbeing | Benchmarking | Action Item | Benchmark with NGPD for their improvement in engagement | Mohammed H. Malki |  |  |  | Q4 2021 | Q4 2021 |  |  | Not Completed |  | Within ETC
109 | People development and Engagment | Emergin Skillsets & Talents | AI Skillsets | Action Item | AI hub Scope | Abdullah Ghamdi (SAPED DM & iScope suprevisor) & Digtalization team |  |  |  | Q4 2021 | Q1 2022 |  |  | Not Completed |  | Within ETC
110 | People development and Engagment | Emergin Skillsets & Talents | AI Skillsets | Action Item | AI Committee formulation | Abdullah Ghamdi (SAPED DM & iScope suprevisor) & Digtalization team |  |  |  | Q4 2021 | Q1 2022 |  |  | Not Completed |  | Within ETC
111 | People development and Engagment | Emergin Skillsets & Talents | AI Skillsets | Action Item | Create AI Survey and get feedback | Abdullah Ghamdi (SAPED DM & iScope suprevisor) & Digtalization team |  |  |  | Q4 2021 | Q1 2022 |  |  | Not Completed |  | Within ETC
112 | People development and Engagment | Emergin Skillsets & Talents | AI Skillsets | Action Item | AI (hub) | Abdullah Ghamdi (SAPED DM & iScope suprevisor) & Digtalization team |  |  |  | Q4 2021 | Q3 2022 |  |  | Not Completed |  | Within ETC
113 | People development and Engagment | Emergin Skillsets & Talents | AI Skillsets | Action Item | deploy AI website and analyze and evaluate submission | Abdullah Ghamdi (SAPED DM & iScope suprevisor) & Digtalization team |  |  |  | Q4 2021 | Q4 2022 |  |  | Not Completed |  | Within ETC
114 | People development and Engagment | Performance & Wellbeing | SAPED Social Meetings | Action Item | Draft process for social exchanges | Abdulrahman Mishkhes |  |  |  | Q4 2021 | Q1 2022 |  |  | Not Completed |  | Within ETC
115 | People development and Engagment | Performance & Wellbeing | Evaluation matrix | Action Item | SAPED HR committee | Completed | [7 empty] | Not Completed |  | Beyond ETC | 0
116 | People development and Engagment | Performance & Wellbeing | Evaluation matrix | Action Item | PMP goals and evaluation | Abdulaziz Shieban and SAPED HR Committee |  |  |  | Q4 2021 | Q3 2022 |  |  | Not Completed |  | Within ETC
117 | People development and Engagment | Performance & Wellbeing | Evaluation matrix | Action Item | Standardize evaluation scheme | Abdulaziz Shieban and SAPED HR Committee |  |  |  | Q4 2021 | Q3 2022 |  |  | Not Completed |  | Within ETC
118 | People development and Engagment | Performance & Wellbeing | Technology and Innovation | Action Item | Formulated Technology & innovation team plan | IPDAA team | [5 empty] | IPDAA team already created |  | Not Completed |  | Beyond ETC | 0
119 | People development and Engagment | Performance & Wellbeing | Technology and Innovation | Action Item | activate technology & innovation teams | IPDAA team | [5 empty] | IPDAA team already created |  | Not Completed |  | Beyond ETC | 0
120 | People development and Engagment | Performance & Wellbeing | Technology and Innovation | Action Item | Analyze innovation submission | IPDAA team |  |  | Monthly |  |  | IPDAA team already created |  | Not Completed |  | Beyond ETC | 0
Formulas:
Due/Not Due = IFERROR(IF([Expected Completion Date (ETC)]="NA","Please add ETC",IF([Expected Completion Date (ETC)]>TODAY(),"Note Due",IF([Expected Completion Date (ETC)]<=TODAY(),"Due"))),"Fix the ETC")
Compliance (within ETC vs beyond ETC) = IF([Expected Completion Date (ETC)]="NA","Please add ETC",IF([Expected Completion Date (ETC)]<TODAY(),IF([Actual Completion Date]="","Beyond ETC",IF([Actual Completion Date]>[Expected Completion Date (ETC)],"Beyond ETC",IF([Actual Completion Date]<=[Expected Completion Date (ETC)],"Within ETC"))),IF([Actual Completion Date]="","Within ETC",IF([Actual Completion Date]<=[Expected Completion Date (ETC)],"Within ETC","Fix Actual completion date"))))
pasted from KPI Columnn H (Strategy owners confused KPI and completion %)

## Pivot. (hidden)
Strategy | Task Category | Tast | Status | Frequency | Product of Target | Product of Actual
Re-Branding
Culture shift trigger
Strategy Roll-out
Not Done
|  |  |  | (blank) | 0
Develop a slogan for the outreach program
Not Done
|  |  |  | (blank) | 0
Outreach program for internally/external costumers (i.e celebrate local and international events, periodical accomplishment newsletter, strategy ordinated messages, and Re-brand Enlight )
Not Done
|  |  |  | (blank) | 0
Synergize with “People” strategy to achieve “buy-in” thru the enhancement of workplace culture
Not Done
|  |  |  | (blank) | 0
Exposure/Footprint
Industry exposure (Number of SAPED SPE contribution)
Not Done
|  |  |  | (blank) | 0
SAPED technical publications (Sandrose, JPT, oil & gas, world oil,…etc)
Not Done
|  |  |  | (blank) | 0
Sponsorship of prestigious events (sponsor a technical OOK booth, one technical event in SAPED operational hubs, one non technical event)
Not Done
|  |  |  | (blank) | 0
Produce SAPED visual content (HSS&E, technical, OE, and promoting SAPED)
Not Done
|  |  |  | (blank) | 0
Awards participating (external/internal)
Not Done
|  |  |  | (blank) | 0
Strategy Fulfilment
Strategy Roll-out campaign
Not Done
|  |  |  | Yearly | 1 | 0
Strategy committee team formation and Dashboard creation
Not Done
|  |  |  | (blank) | 0
Budgeting and utilization of strategies' related resources
Not Done
|  |  |  | (blank) | 0
Meeting with strategy owners to measure (progress %)
Not Done
|  |  |  | (blank) | 0
Notes:
-Don't do functions just fix the look
-Add Ghantt Chart
-Try the sunburst it has good potential
-Check with Ahmed Mousa

## Data
Number | Organization | Process | Source | Action Item | Criteria | Assignee | Start Date | Due Date | Status |  | History | Summary | Count | Closed | Completion % | Closed | Completed (Not Verified) | In-Progress | Not-Started | Overdue | Fill |  | End Points
387244 | SAPED | 7.1 Cost Efficiency Strategy | Other | Culture Creation: Perform a Finance Workshop with key SAPED and SAWCOD members | Plan | Abdulmohsin, Yousif A | 2022-09-09 | 2022-11-30 | Overdue | 0 | history | Re-Branding | 57 | 4 | 7.018% | 4 | 0 | 0 | 13 | 40 | 92.98% | 7.018% | X | Y
387210 | SAPED | 7.1 Digitization Strategy | Other | Remote Assistance & Virtual: Broadband Equipment Installation for SAWCOD Sites (2022) | Plan | Ajmi, Fahad M | 2021-12-01 | 2022-12-29 | Overdue | 0 | history | Strategy Fulfilment | 30 | 4 | 13.33% | 4 | 0 | 0 | 13 | 13 | 86.67% | 13.33% | 0 | 1
378704 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: Strategies Achievement Report - Finalize Report format with CST | Plan | Ajmi, Fahad M | 2022-11-01 | 2022-11-30 | Overdue | 0 | history | Culture Shift Trigger | 14 | 0 | 0% | 0 | 0 | 0 | 0 | 14 | 100% | 0% | -0.42678 | 0.90436
378705 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: Strategies Achievement Report - Contact Strategy to highlight their achievement | Plan | Ajmi, Fahad M | 2022-12-01 | 2022-12-31 | Overdue | 0 | history | Exposure/Footprint | 13 | 0 | 0% | 0 | 0 | 0 | 0 | 13 | 100% | 0% | X | Y
387208 | SAPED | 7.1 Digitization Strategy | Other | Administrative Compliance Tools: Oil Target Process | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-12-29 | Overdue | 0 | history | Cost Efficiency | 15 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0 | 1
387191 | SAPED | 7.1 Digitization Strategy | Other | Production Optimization: Gas Lift Monitoring & Optimization - PEACE (2022) | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-12-29 | Overdue | 0 | history | Value Creation | 8 | 0 | 0% | 0 | 4 | 0 | 0 | 4 | 100% | 0% | 0 | 1
378711 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: SAPED Annual Event - Finalize event agenda | Plan | Ajmi, Fahad M | 2022-10-15 | 2022-11-20 | Overdue | 0 | history | Cost Intelligence Hub | 3 | 0 | 0% | 0 | 2 | 0 | 0 | 1 | 100% | 0% | X | Y
387209 | SAPED | 7.1 Digitization Strategy | Other | Administrative Compliance Tools: target automation | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-12-29 | Overdue | 0 | history | Culture Creation | 4 | 0 | 0% | 0 | 1 | 0 | 0 | 3 | 100% | 0% | 0 | 1
378712 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: SAPED Annual Event | Plan | Ajmi, Fahad M | 2022-12-01 | 2022-12-31 | Overdue | 0 | history | Sustainability | 27 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0 | 1
387211 | SAPED | 7.1 Digitization Strategy | Other | Well Integrity Assurance: Corrosion Control and Advisory system (enhancement) | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-12-29 | Overdue | 0 | history | Environmental Stewardship | 23 | 0 | 0% | 0 | 0 | 14 | 6 | 3 | 100% | 0% | X | Y
387203 | SAPED | 7.1 Digitization Strategy | Other | Administrative Compliance Tools: Production Engineering Data Compliance Engine Risk Ranking | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-12-29 | Overdue | 0 | history | Production & Integrity | 4 | 0 | 0% | 0 | 0 | 3 | 0 | 1 | 100% | 0% | 0 | 1
387189 | SAPED | 7.1 Digitization Strategy | Other | Production Optimization: Multi-phase virtual Metering and Prediction (2022) | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-12-29 | Overdue | 0 | history | People development and Engagment | 23 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0 | 1
378703 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: Strategies Achievement Report - Identify Reported items for our strategy | Plan | Ajmi, Fahad M | 2022-10-01 | 2022-12-31 | Overdue | 0 | history | Employee Wellbeing | 3 | 0 | 0% | 0 | 0 | 0 | 0 | 3 | 100% | 0% | X | Y
387206 | SAPED | 7.1 Digitization Strategy | Other | Production Optimization: (PEACE) AI/ML Well Rate Validation | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-12-29 | Overdue | 0 | history | T&D Administration & Oversigh | 12 | 0 | 0% | 0 | 0 | 0 | 0 | 12 | 100% | 0% | 0 | 1
387187 | SAPED | 7.1 Digitization Strategy | Other | Remote Assistance & Virtual: Remote Job Witnessing (2022) | Plan | Ajmi, Fahad M | 2021-01-01 | 2022-12-29 | Overdue | 0 | history | Employee Performance & Engagement | 8 | 0 | 0% | 0 | 0 | 0 | 0 | 8 | 100% | 0% | 0 | 1
387188 | SAPED | 7.1 Digitization Strategy | Other | Well Integrity Assurance: Real time Well Integrity Identification -- Annuli Orion | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-12-29 | Overdue | 0 | history | Digitization | 78 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 100% | 0% | X | Y
387193 | SAPED | 7.1 Digitization Strategy | Other | Production Optimization: PI/II estimation/ ESP optimization ...... | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-12-29 | Overdue | 0 | history | Production Optimization | 20 | 1 | 5% | 1 | 7 | 5 | 2 | 5 | 95% | 5% | 0 | 1
378709 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: SAPED Annual Event - Confirm event date & Location | Plan | Ajmi, Fahad M | 2022-08-01 | 2022-12-31 | Overdue | 0 | history | Administrative Compliance Tools | 25 | 1 | 4% | 1 | 13 | 5 | 0 | 6 | 96% | 4% | -0.088071 | 0.99611
378710 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: SAPED Annual Event - Book Venue | Plan | Ajmi, Fahad M | 2022-10-01 | 2022-11-30 | Overdue | 0 | history | Remote Assistance & Virtual | 6 | 0 | 0% | 0 | 3 | 1 | 0 | 2 | 100% | 0%
387202 | SAPED | 7.1 Digitization Strategy | Other | Administrative Compliance Tools: Avails Enhancement (2022) | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-12-29 | Overdue | 0 | history | Data Validity/Reliability | 7 | 0 | 0% | 0 | 5 | 2 | 0 | 0 | 100% | 0%
378706 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: Strategies Achievement Report - implement chapter into SAPED Book | Plan | Ajmi, Fahad M | 2023-01-01 | 2023-01-31 | Overdue | 0 | history | Well Integrity Assurance | 18 | 0 | 0% | 0 | 10 | 3 | 1 | 4 | 100% | 0%
387207 | SAPED | 7.1 Digitization Strategy | Other | Administrative Compliance Tools: Automation of Access Authority ( RBAC) ( 2022) | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-12-29 | Overdue | 0 | history | Total | 200 | 4 | 1.404% | 4 | 0 | 0 | 13 | 40 | 98.6% | 1.404%
387185 | SAPED | 7.1 Digitization Strategy | Other | Administrative Compliance Tools: Well IP Enhancement | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-12-29 | Overdue | 0 | history
387186 | SAPED | 7.1 Digitization Strategy | Other | Project : Well IP Enhancement | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-12-29 | Overdue | 0 | history
378707 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: Strategies Achievement Report - Finalize chapter | Plan | Ajmi, Fahad M | 2023-01-01 | 2023-01-31 | Overdue | 0 | history
378713 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: SAPED Annual Event - Gifts/Awards selection through vendor bidding | Plan | Ajmi, Fahad M | 2022-12-01 | 2023-01-31 | Overdue | 0 | history
387192 | SAPED | 7.1 Digitization Strategy | Other | Well Integrity Assurance: Real time visualization and downhole leak | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-12-29 | Overdue | 0 | history
387184 | SAPED | 7.1 Digitization Strategy | Other | Well Integrity Assurance: MIT Logs Capturing | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-12-01 | Overdue | 0 | history
387190 | SAPED | 7.1 Digitization Strategy | Other | Production Optimization: (PEACE) Smart Wells Production Optimization | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-12-29 | Overdue | 0 | history
387239 | SAPED | 7.1 Cost Efficiency Strategy | Other | Value Creation: Prepare and issue quarterly SAPED Cost Efficiency Report. | Plan | Alameer, Mohammed A | 2022-01-07 | 2022-10-06 | Overdue | 0 | history
381856 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | culture shift trigger: SAPED facts - "SAPED facts" general template | Plan | Aldughaither, Abdulaziz E | 2022-10-01 | 2022-12-31 | Overdue | 0 | history
381859 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | culture shift trigger: SAPED facts - send to SAPED all as a Flyer | Plan | Aldughaither, Abdulaziz E | 2022-10-01 | 2022-12-31 | Overdue | 0 | history
381860 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | culture shift trigger: SAPED facts - Create a QR code to illustrate “SAPED overview” | Plan | Aldughaither, Abdulaziz E | 2022-10-01 | 2022-12-31 | Overdue | 0 | history
381863 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | culture shift trigger: Wall of Fame - Create a QR Code | Plan | Aldughaither, Abdulaziz E | 2022-11-01 | 2022-12-31 | Overdue | 0 | history
381857 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | culture shift trigger: SAPED facts - Collect facts & technical data | Plan | Aldughaither, Abdulaziz E | 2022-10-01 | 2022-12-31 | Overdue | 0 | history
381858 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | culture shift trigger: SAPED facts - Filter collected facts | Plan | Aldughaither, Abdulaziz E | 2022-10-01 | 2022-12-31 | Overdue | 0 | history
381861 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | culture shift trigger: Wall of Fame - Work with office services to assign location | Plan | Aldughaither, Abdulaziz E | 2022-10-01 | 2022-12-31 | Overdue | 0 | history
381862 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | culture shift trigger: Wall of Fame - Selection Criteria | Plan | Aldughaither, Abdulaziz E | 2022-11-01 | 2022-12-31 | Overdue | 0 | history
387269 | SAPED | 7.1 Sustainability Strategy | Other | Environmental Stewardship: Zero Flaring - Assessment of current flaring | Plan | Alharbi, Ayman N | 2022-08-01 | 2022-10-31 | Overdue | 0 | history
387242 | SAPED | 7.1 Cost Efficiency Strategy | Other | Culture Creation: Tailor a Finance Workshop for SAPED all to spread out the financial awareness | Plan | Khamees, Abdullah J | 2022-07-07 | 2022-10-31 | Overdue | 0 | history
387243 | SAPED | 7.1 Cost Efficiency Strategy | Other | Culture Creation: Explore a Finance Course to be taken by SAPED All to enhance the financial culture | Plan | Alkhaldi, Abdullah M | 2022-06-06 | 2022-11-25 | Overdue | 0 | history
387238 | SAPED | 7.1 Cost Efficiency Strategy | Other | Value Creation: Prepare and issue monthly SAPED Financial Flyer. | Plan | Almannai, Mohammed N | 2022-08-07 | 2022-12-31 | Overdue | 0 | history
378729 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: SAPED SHAREK - update mission & vision and other taps | Plan | Abubakralmulla, Aishah A | 2022-10-01 | 2022-12-31 | Overdue | 0 | history
378727 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: SAPED SHAREK- Update SAPED strategy section | Plan | Abubakralmulla, Aishah A | 2022-08-01 | 2022-12-30 | Overdue | 0 | history
381866 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | culture shift trigger: Media & Tracking - Set submission targets (for SAPED) | Plan | Almuaibid, Abdulrahman F | 2022-11-01 | 2022-12-31 | Overdue | 0 | history
381864 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | culture shift trigger: Media & Tracking - Capitalize on existing SAPED publications & media | Plan | Almuaibid, Abdulrahman F | 2022-11-01 | 2022-12-31 | Overdue | 0 | history
381868 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | culture shift trigger: SAPED facts - Creating a Template | Plan | Almuaibid, Abdulrahman F | 2022-11-01 | 2022-12-31 | Overdue | 0 | history
381865 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | culture shift trigger: Media & Tracking - Ensuring that the review of governing documents | Plan | Almuaibid, Abdulrahman F | 2022-11-01 | 2022-12-31 | Overdue | 0 | history
381869 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | culture shift trigger: SAPED facts - A bank of facts must be generated and stored | Plan | Almuaibid, Abdulrahman F | 2022-11-01 | 2022-12-31 | Overdue | 0 | history
381867 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | culture shift trigger: Media & Tracking - Standardizing and advertising for the use of publication | Plan | Almuaibid, Abdulrahman F | 2022-11-01 | 2022-12-31 | Overdue | 0 | history
387272 | SAPED | 7.1 Sustainability Strategy | Other | Environmental Stewardship: SeaWater Intervention - rigless operation activities | Plan | Alnaim, Mohammed F | 2022-10-01 | 2023-01-31 | Overdue | 0 | history
378734 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Exposure/Footprint: Knowledge Exchange Event/Forum - Create invitation Template | Plan | Alsunnary, Khaled J | 2022-10-02 | 2022-12-31 | Overdue | 0 | history
378730 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Exposure/Footprint: Award Participation - Create Announcement Template for All Awards | Plan | Alsunnary, Khaled J | 2022-10-02 | 2022-12-31 | Overdue | 0 | history
378737 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Exposure/Footprint: Knowledge Exchange Event/Forum - Update the KPI once events are identified | Plan | Alsunnary, Khaled J | 2022-10-02 | 2022-12-31 | Overdue | 0 | history
378739 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Exposure/Footprint: Outreach Program - Identify and distribute outreach Events for 2023 | Plan | Alsunnary, Khaled J | 2022-10-02 | 2022-12-31 | Overdue | 0 | history
378732 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Exposure/Footprint: Knowledge Exchange Event/Forum - Identify Events for 2023 | Plan | Alsunnary, Khaled J | 2022-10-02 | 2022-12-31 | Overdue | 0 | history
378746 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Exposure/Footprint: Conducting Industrial Visits - Create Template for Industrial Events | Plan | Alsunnary, Khaled J | 2022-10-02 | 2022-12-31 | Overdue | 0 | history
378731 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Exposure/Footprint: Award Participation - Create Announcement Template for Winning Awards | Plan | Alsunnary, Khaled J | 2022-10-02 | 2022-12-31 | Overdue | 0 | history
378736 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Exposure/Footprint: Knowledge Exchange Event/Forum - Create Semi-Annual Announcement Template | Plan | Alsunnary, Khaled J | 2022-10-02 | 2022-12-31 | Overdue | 0 | history
378735 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Exposure/Footprint: Knowledge Exchange Event/Forum - Identify Semi-Annual forum for 2023 | Plan | Alsunnary, Khaled J | 2022-10-02 | 2022-12-31 | Overdue | 0 | history
378738 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Exposure/Footprint: Outreach Program - Identify SAPED outreach participants for 2023 | Plan | Alsunnary, Khaled J | 2022-10-02 | 2022-12-31 | Overdue | 0 | history
378745 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Exposure/Footprint: Conducting Industrial Visits - Identify Events for 2023 | Plan | Alsunnary, Khaled J | 2022-10-02 | 2022-12-31 | Overdue | 0 | history
378748 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Exposure/Footprint: Conducting Industrial Visits - Update the KPI once events are identified | Plan | Alsunnary, Khaled J | 2022-10-02 | 2022-12-31 | Overdue | 0 | history
378742 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Exposure/Footprint: Outreach Program - Update the KPI and action items once events are identified | Plan | Alsunnary, Khaled J | 2022-10-02 | 2022-12-31 | Overdue | 0 | history
387270 | SAPED | 7.1 Sustainability Strategy | Other | Environmental Stewardship: Reduced Ground Water Fracturing - Tabulation | Plan | Daghriri, Majed H | 2022-01-01 | 2022-09-30 | Overdue | 0 | history
378728 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: SAPED SHAREK - update Manager message | Plan | Dhahrani, Fatimah H | 2022-10-01 | 2022-12-31 | Overdue | 0 | history
387259 | SAPED | 7.1 People Development & Engagement Strategy | Other | T&D Administration & Talents Oversight: Skillset Evaluation & Expansion - 2 | Plan | Ghanmi, Ahmed A | 2022-01-01 | 2022-12-31 | Overdue | 0 | history
387262 | SAPED | 7.1 People Development & Engagement Strategy | Other | T&D Administration & Talents Oversight: Leadership Development Enhancement - 2 | Plan | Ghanmi, Ahmed A | 2022-01-01 | 2022-12-31 | Overdue | 0 | history
387263 | SAPED | 7.1 People Development & Engagement Strategy | Other | T&D Administration & Talents Oversight: Centralized Governance and Monitoring Entity - 1 | Plan | Ghanmi, Ahmed A | 2022-01-01 | 2022-12-31 | Overdue | 0 | history
387264 | SAPED | 7.1 People Development & Engagement Strategy | Other | T&D Administration & Talents Oversight: Continues Improvement - Conduct benchmarking | Plan | Ghanmi, Ahmed A | 2022-01-01 | 2022-12-31 | Overdue | 0 | history
387246 | SAPED | 7.1 People Development & Engagement Strategy | Other | T&D Administration & Talents Oversight: Centralized Governance and Monitoring Entity - 2 | Plan | Ghanmi, Ahmed A | 2022-01-01 | 2022-12-31 | Overdue | 0 | history
387257 | SAPED | 7.1 People Development & Engagement Strategy | Other | T&D Administration & Talents Oversight: Leadership Development Enhancement - 1 | Plan | Ghanmi, Ahmed A | 2022-01-01 | 2022-12-31 | Overdue | 0 | history
387267 | SAPED | 7.1 People Development & Engagement Strategy | Other | T&D Administration & Talents Oversight: Centralized Governance and Monitoring Entity - 3 | Plan | Ghanmi, Ahmed A | 2022-01-01 | 2022-12-31 | Overdue | 0 | history
387255 | SAPED | 7.1 People Development & Engagement Strategy | Other | T&D Administration & Talents Oversight: Skillset Evaluation & Expansion - 1 | Plan | Ghanmi, Ahmed A | 2022-01-01 | 2022-12-31 | Overdue | 0 | history
387250 | SAPED | 7.1 People Development & Engagement Strategy | Other | T&D Administration & Talents Oversight: Fit-for-Purpose Development Programs - 2 | Plan | Ghanmi, Ahmed A | 2022-01-01 | 2022-12-31 | Overdue | 0 | history
387268 | SAPED | 7.1 People Development & Engagement Strategy | Other | T&D Administration & Talents Oversight: Training Resources oversight - 1 | Plan | Ghanmi, Ahmed A | 2022-01-01 | 2022-12-31 | Overdue | 0 | history
387249 | SAPED | 7.1 People Development & Engagement Strategy | Other | T&D Administration & Talents Oversight: Fit-for-Purpose Development Programs - 1 | Plan | Ghanmi, Ahmed A | 2022-01-01 | 2022-12-31 | Overdue | 0 | history
387265 | SAPED | 7.1 People Development & Engagement Strategy | Other | T&D Administration & Talents Oversight: Continues Improvement - Review the yearly strategy roadmap | Plan | Ghanmi, Ahmed A | 2022-01-01 | 2022-12-31 | Overdue | 0 | history
387271 | SAPED | 7.1 Sustainability Strategy | Other | Production & Integrity: Network Optimizer - Establish A master sheet | Plan | Khunaizi, Mohammed N | 2022-09-01 | 2022-11-30 | Overdue | 0 | history
387253 | SAPED | 7.1 People Development & Engagement Strategy | Other | Employee Performance & Engagement: Performance Dialog Meeting Quality Enrichment - 3 | Plan | Mishkhes, Abdulrahman T | 2022-01-01 | 2022-12-31 | Overdue | 0 | history
387252 | SAPED | 7.1 People Development & Engagement Strategy | Other | Employee Performance & Engagement: SAPED HR Outreach Program - 2 | Plan | Mishkhes, Abdulrahman T | 2022-01-01 | 2022-12-31 | Overdue | 0 | history
387248 | SAPED | 7.1 People Development & Engagement Strategy | Other | Employee Performance & Engagement: Performance Dialog Meeting Quality Enrichment - 4 | Plan | Mishkhes, Abdulrahman T | 2022-01-01 | 2022-12-31 | Overdue | 0 | history
387260 | SAPED | 7.1 People Development & Engagement Strategy | Other | Employee Performance & Engagement: Performance Dialog Meeting Quality Enrichment - 2 | Plan | Mishkhes, Abdulrahman T | 2022-01-01 | 2022-12-31 | Overdue | 0 | history
387251 | SAPED | 7.1 People Development & Engagement Strategy | Other | Employee Performance & Engagement: SAPED HR Outreach Program - 1 | Plan | Mishkhes, Abdulrahman T | 2022-01-01 | 2022-12-31 | Overdue | 0 | history
387266 | SAPED | 7.1 People Development & Engagement Strategy | Other | Employee Performance & Engagement: Employee Engagement Venues - 1 | Plan | Mishkhes, Abdulrahman T | 2022-01-01 | 2022-12-31 | Overdue | 0 | history
387247 | SAPED | 7.1 People Development & Engagement Strategy | Other | Employee Performance & Engagement: Employee Engagement Venues - 2 | Plan | Mishkhes, Abdulrahman T | 2022-01-01 | 2022-12-31 | Overdue | 0 | history
387256 | SAPED | 7.1 People Development & Engagement Strategy | Other | Employee Performance & Engagement: Performance Dialog Meeting Quality Enrichment - 1 | Plan | Mishkhes, Abdulrahman T | 2022-01-01 | 2022-12-31 | Overdue | 0 | history
387245 | SAPED | 7.1 Cost Efficiency Strategy | Other | Cost Intelligent Hub: Develop Data Analysis Model for DCC, BIs, Contingency jobs | Plan | Mousa, Ahmad M | 2022-10-07 | 2022-12-31 | Overdue | 0 | history
387258 | SAPED | 7.1 People Development & Engagement Strategy | Other | Employee Wellbeing: SAPED Wellbeing Program - 1 | Plan | Mukhles, Amro E. | 2022-01-01 | 2022-12-31 | Overdue | 0 | history
387261 | SAPED | 7.1 People Development & Engagement Strategy | Other | Employee Wellbeing: Your Voice Counts; SAPED Cares | Plan | Mukhles, Amro E. | 2022-01-01 | 2022-12-31 | Overdue | 0 | history
387254 | SAPED | 7.1 People Development & Engagement Strategy | Other | Employee Wellbeing: SAPED Wellbeing Program - 2 | Plan | Mukhles, Amro E. | 2022-01-01 | 2022-12-31 | Overdue | 0 | history
387241 | SAPED | 7.1 Cost Efficiency Strategy | Other | Value Creation: Conduct Cost Benefit Analysis (CBA) for 2022 SAPED | Plan | Sabeela, Yousef I | 2022-01-07 | 2022-10-26 | Overdue | 0 | history
387240 | SAPED | 7.1 Cost Efficiency Strategy | Other | Value Creation: Perform a Revenue Generation (RG) Analysis for Oil & Gas Gains. | Plan | Sabeela, Yousef I | 2022-08-07 | 2022-10-06 | Overdue | 0 | history
387213 | SAPED | 7.1 Digitization Strategy | Other | Well Integrity Assurance: WIWL Corrective Actions Advisor (2023) | Plan | Ajmi, Fahad M | 2023-01-01 | 2023-12-30 | In Progress | 0 | history
387212 | SAPED | 7.1 Digitization Strategy | Other | Data Validity/Reliability: Orion 4.0 | Plan | Ajmi, Fahad M | 2021-01-01 | 2024-12-31 | In Progress | 0 | history
387277 | SAPED | 7.1 Sustainability Strategy | Other | Environmental Stewardship: Operational Efficiency Enablers - Quantify CO2 emission | Plan | Alharbi, Ayman N | 2022-11-01 | 2023-03-31 | In Progress | 0 | history
387282 | SAPED | 7.1 Sustainability Strategy | Other | Environmental Stewardship: Zero Flaring - ‘reduce-eliminate’ flaring for all fracturing operations | Plan | Alharbi, Ayman N | 2023-01-01 | 2023-07-31 | In Progress | 0 | history
387276 | SAPED | 7.1 Sustainability Strategy | Other | Environmental Stewardship: Zero Flaring - Establish a strategy of ‘reduce-eliminate’ non-fracturing | Plan | Alharbi, Ayman N | 2022-11-01 | 2023-03-31 | In Progress | 0 | history
387280 | SAPED | 7.1 Sustainability Strategy | Other | Environmental Stewardship: Zero Flaring - assessment of logical and economic viability | Plan | Alharbi, Ayman N | 2023-01-01 | 2023-07-01 | In Progress | 0 | history
387285 | SAPED | 7.1 Sustainability Strategy | Other | Environmental Stewardship: Operational Efficiency Enablers - Improve efficiency multi-lateral access | Plan | Alharbi, Ayman N | 2023-01-01 | 2023-09-30 | In Progress | 0 | history
387284 | SAPED | 7.1 Sustainability Strategy | Other | Environmental Stewardship: Operational Efficiency Enablers - Evaluate the market for Ball Sealers | Plan | Alharbi, Ayman N | 2023-07-01 | 2023-09-30 | In Progress | 0 | history
387279 | SAPED | 7.1 Sustainability Strategy | Other | Environmental Stewardship: SeaWater Intervention - Evaluate water for CT | Plan | Alnaim, Mohammed F | 2023-02-01 | 2023-06-30 | In Progress | 0 | history
387273 | SAPED | 7.1 Sustainability Strategy | Other | Environmental Stewardship: Reduced Ground Water Fracturing - Finalize the feasibility review | Plan | Daghriri, Majed H | 2022-10-01 | 2023-02-28 | In Progress | 0 | history
387289 | SAPED | 7.1 Sustainability Strategy | Other | Environmental Stewardship: Reduced Ground Water Fracturing - Tracking | Plan | Daghriri, Majed H | 2022-09-01 | 2023-12-31 | In Progress | 0 | history
387274 | SAPED | 7.1 Sustainability Strategy | Other | Environmental Stewardship: Reduced Ground Water Fracturing - Forecasting | Plan | Daghriri, Majed H | 2023-01-01 | 2023-02-28 | In Progress | 0 | history
387286 | SAPED | 7.1 Sustainability Strategy | Other | Production & Integrity: Network Optimizer - Utilize model | Plan | Khunaizi, Mohammed N | 2023-01-01 | 2023-09-30 | In Progress | 0 | history
387275 | SAPED | 7.1 Sustainability Strategy | Other | Production & Integrity: Network Optimizer - Identify transfer lines | Plan | Khunaizi, Mohammed N | 2022-11-30 | 2023-03-31 | In Progress | 0 | history
387283 | SAPED | 7.1 Sustainability Strategy | Other | Production & Integrity: Network Optimizer - maintain model | Plan | Khunaizi, Mohammed N | 2023-01-01 | 2023-09-30 | In Progress | 0 | history
387292 | SAPED | 7.1 Sustainability Strategy | Other | Environmental Stewardship: Artificial Operations - Develop Frac Database | Plan | Mukhtar, Mohammed A | 2022-10-01 | 2023-12-31 | In Progress | 0 | history
387291 | SAPED | 7.1 Sustainability Strategy | Other | Environmental Stewardship: Artificial Operations - Develop Proppant & Fluids Advisors | Plan | Mukhtar, Mohammed A | 2022-10-01 | 2023-12-31 | In Progress | 0 | history
387288 | SAPED | 7.1 Sustainability Strategy | Other | Environmental Stewardship: Artificial Operations - Develop CT advisor | Plan | Mukhtar, Mohammed A | 2022-10-01 | 2023-12-31 | In Progress | 0 | history
387290 | SAPED | 7.1 Sustainability Strategy | Other | Environmental Stewardship: Artificial Operations - Develop Fishing Advisor | Plan | Mukhtar, Mohammed A | 2022-10-01 | 2023-12-31 | In Progress | 0 | history
387223 | SAPED | 7.1 Digitization Strategy | Other | Administrative Compliance Tools: Live EWAM & WDB Integration (2023) | Plan | Omran, Mohammad R | 2023-01-01 | 2023-12-31 | In Progress | 0 | history
387217 | SAPED | 7.1 Digitization Strategy | Other | Production Optimization: ESP Advisory system (2023) | Plan | Omran, Mohammad R | 2022-01-01 | 2023-12-31 | In Progress | 0 | history
387214 | SAPED | 7.1 Digitization Strategy | Other | Production Optimization: (PEACE) SBHP estimation / Critical rate estimation/ Field rate estimation | Plan | Omran, Mohammad R | 2022-01-01 | 2023-12-31 | In Progress | 0 | history
387219 | SAPED | 7.1 Digitization Strategy | Other | Remote Assistance & Virtual: AR/VR Applications (2023) | Plan | Omran, Mohammad R | 2022-01-01 | 2023-12-31 | In Progress | 0 | history
387226 | SAPED | 7.1 Digitization Strategy | Other | Production Optimization: (PEACE) Well Rate Allocation (2023) | Plan | Omran, Mohammad R | 2023-01-01 | 2023-12-31 | In Progress | 0 | history
387218 | SAPED | 7.1 Digitization Strategy | Other | Administrative Compliance Tools: Production Engineering Data Compliance Engine Passing Valves (2023) | Plan | Omran, Mohammad R | 2022-01-01 | 2023-12-31 | In Progress | 0 | history
387221 | SAPED | 7.1 Digitization Strategy | Other | Administrative Compliance Tools: Production Engineering Data Compliance Engine Well Status (2023) | Plan | Omran, Mohammad R | 2023-01-01 | 2023-12-31 | In Progress | 0 | history
387225 | SAPED | 7.1 Digitization Strategy | Other | Administrative Compliance Tools: Production Engineering Data Compliance Engine WIWL (2023) | Plan | Omran, Mohammad R | 2023-01-01 | 2023-12-31 | In Progress | 0 | history
387224 | SAPED | 7.1 Digitization Strategy | Other | Well Integrity Assurance: Scale prediction or tendency (2023) | Plan | Omran, Mohammad R | 2023-01-01 | 2023-12-31 | In Progress | 0 | history
387215 | SAPED | 7.1 Digitization Strategy | Other | Data Validity/Reliability: Real-time Plants allocation (2023) | Plan | Omran, Mohammad R | 2022-01-01 | 2023-12-31 | In Progress | 0 | history
387222 | SAPED | 7.1 Digitization Strategy | Other | Well Integrity Assurance: Synthetic Corrosion Log Phase-2 (2023) | Plan | Omran, Mohammad R | 2023-01-01 | 2023-12-31 | In Progress | 0 | history
387229 | SAPED | 7.1 Digitization Strategy | Other | Administrative Compliance Tools: WDB Activities Automation Project Remove Duplicate Activities | Plan | Omran, Mohammad R | 2023-01-01 | 2023-12-31 | In Progress | 0 | history
387220 | SAPED | 7.1 Digitization Strategy | Other | Production Optimization: Bubble point monitoring (PEACE) 2023 | Plan | Omran, Mohammad R | 2023-01-01 | 2023-12-31 | In Progress | 0 | history
387216 | SAPED | 7.1 Digitization Strategy | Other | Production Optimization: Frac database (2023) | Plan | Omran, Mohammad R | 2022-01-01 | 2023-12-31 | In Progress | 0 | history
378708 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: Strategies Achievement Report - Issue Chapter | Plan | Ajmi, Fahad M | 2023-02-01 | 2023-02-28 | Not Started | 0 | history
378726 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: SAPED Annual Event - Host Event | Plan | Ajmi, Fahad M | 2023-06-01 | 2023-06-30 | Not Started | 0 | history
378719 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: SAPED Annual Event - Announce Event | Plan | Ajmi, Fahad M | 2023-05-01 | 2023-05-10 | Not Started | 0 | history
378716 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: SAPED Annual Event - Confirm VIP List | Plan | Ajmi, Fahad M | 2023-02-01 | 2023-03-31 | Not Started | 0 | history
377900 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: Tracking Dashboard - Monitor Tracking dashboard for the strategies | Plan | Ajmi, Fahad M | 2022-12-01 | 2023-03-31 | Not Started | 0 | history
378722 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: SAPED Annual Event - Dry run with presenters | Plan | Ajmi, Fahad M | 2023-05-01 | 2023-05-18 | Not Started | 0 | history
378715 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: SAPED Annual Event - contact Ithra for Entertainment section | Plan | Ajmi, Fahad M | 2023-01-01 | 2023-02-28 | Not Started | 0 | history
378723 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: SAPED Annual Event - contact catering companies | Plan | Ajmi, Fahad M | 2023-05-01 | 2023-05-31 | Not Started | 0 | history
378718 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: SAPED Annual Event - select guest speaker and send invitation letters | Plan | Ajmi, Fahad M | 2023-04-01 | 2023-04-30 | Not Started | 0 | history
378724 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: SAPED Annual Event - Finalize overall cost | Plan | Ajmi, Fahad M | 2023-05-01 | 2023-06-08 | Not Started | 0 | history
378717 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: SAPED Annual Event - send letter to VIP's | Plan | Ajmi, Fahad M | 2023-04-01 | 2023-04-16 | Not Started | 0 | history
378714 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: SAPED Annual Event - contact vendors for photographer & video personnel | Plan | Ajmi, Fahad M | 2023-01-01 | 2023-02-28 | Not Started | 0 | history
387294 | SAPED | 7.1 Sustainability Strategy | Other | Environmental Stewardship: Zero Flaring - Amend existing SOPs | Plan | Alharbi, Ayman N | 2023-04-01 | 2023-12-31 | Not Started | 0 | history
387293 | SAPED | 7.1 Sustainability Strategy | Other | Environmental Stewardship: Operational Efficiency Enablers - Determine the reduction in CO2 emission | Plan | Alharbi, Ayman N | 2023-10-01 | 2023-12-31 | Not Started | 0 | history
387281 | SAPED | 7.1 Sustainability Strategy | Other | Environmental Stewardship: Operational Efficiency Enablers - Explore Innovative Ideas | Plan | Alharbi, Ayman N | 2023-04-01 | 2023-07-01 | Not Started | 0 | history
387295 | SAPED | 7.1 Sustainability Strategy | Other | Environmental Stewardship: SeaWater Intervention - Quantify Ground water Savings. | Plan | Alnaim, Mohammed F | 2023-11-01 | 2024-02-01 | Not Started | 0 | history
387287 | SAPED | 7.1 Sustainability Strategy | Other | Environmental Stewardship: SeaWater Intervention - Reflect seawater in PE issued programs. | Plan | Alnaim, Mohammed F | 2023-07-01 | 2023-12-31 | Not Started | 0 | history
387278 | SAPED | 7.1 Sustainability Strategy | Other | Environmental Stewardship: Reduced Ground Water Fracturing - Publication & Sharing | Plan | Daghriri, Majed H | 2023-03-01 | 2023-06-30 | Not Started | 0 | history
378720 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: SAPED Annual Event - prepare manager script | Plan | Dhahrani, Fatimah H | 2023-05-01 | 2023-05-21 | Not Started | 0 | history
387227 | SAPED | 7.1 Digitization Strategy | Other | Production Optimization: Field potential estimation / Bottleneck identification (PEACE)- 2024 | Plan | Omran, Mohammad R | 2024-01-01 | 2024-12-31 | Not Started | 0 | history
387228 | SAPED | 7.1 Digitization Strategy | Other | Well Integrity Assurance: Well-head tree valve Failure Prediction (2024) | Plan | Omran, Mohammad R | 2024-01-01 | 2024-12-31 | Not Started | 0 | history
387230 | SAPED | 7.1 Digitization Strategy | Other | Production Optimization: PI/II Candidate Evaluator (2024) | Plan | Omran, Mohammad R | 2024-01-01 | 2024-12-31 | Not Started | 0 | history
387204 | SAPED | 7.1 Digitization Strategy | Other | Data Validity/Reliability: ICV Data Management (data, gain,etc) (2022) | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-12-29 | Complete | 0 | history
387173 | SAPED | 7.1 Digitization Strategy | Other | Remote Assistance & Virtual: Adoption of Virtual Video Conferencing in iSCOPE (2021) | Plan | Ajmi, Fahad M | 2021-01-01 | 2021-12-01 | Complete | 0 | history
387201 | SAPED | 7.1 Digitization Strategy | Other | Administrative Compliance Tools: Production Engineering Data Compliance Engine Zero TCA | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-12-29 | Complete | 0 | history
387180 | SAPED | 7.1 Digitization Strategy | Other | Administrative Compliance Tools: Well Custodianship Transfer | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-02-01 | Complete | 0 | history
387168 | SAPED | 7.1 Digitization Strategy | Other | Production Optimization: Well Network Modeling ( Kh & CA PIPESIM 2021) | Plan | Ajmi, Fahad M | 2021-01-01 | 2021-09-01 | Complete | 0 | history
387156 | SAPED | 7.1 Digitization Strategy | Other | Administrative Compliance Tools: WOCP Enhancement | Plan | Ajmi, Fahad M | 2020-01-01 | 2020-12-01 | Complete | 0 | history
387166 | SAPED | 7.1 Digitization Strategy | Other | Administrative Compliance Tools: WDB Activities Automation Project | Plan | Ajmi, Fahad M | 2021-01-01 | 2021-07-01 | Complete | 0 | history
387205 | SAPED | 7.1 Digitization Strategy | Other | Administrative Compliance Tools: WDB Activities Automation Project Validity Change Request | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-12-29 | Complete | 0 | history
387169 | SAPED | 7.1 Digitization Strategy | Other | Data Validity/Reliability: Well Operating Status Prediction (2021) | Plan | Ajmi, Fahad M | 2021-01-01 | 2021-09-01 | Complete | 0 | history
387182 | SAPED | 7.1 Digitization Strategy | Other | Administrative Compliance Tools: Compliance Engine Missing Well Intervention Data | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-06-12 | Complete | 0 | history
387197 | SAPED | 7.1 Digitization Strategy | Other | Well Integrity Assurance: Risk ranking (enhancement) | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-12-29 | Complete | 0 | history
387183 | SAPED | 7.1 Digitization Strategy | Other | Administrative Compliance Tools: Production Engineering Data Compliance Engine Locked Potential | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-06-12 | Complete | 0 | history
387178 | SAPED | 7.1 Digitization Strategy | Other | Well Integrity Assurance: Smart Survey Validation ( Annuli Survey) | Plan | Ajmi, Fahad M | 2021-01-01 | 2021-12-29 | Complete | 0 | history
387195 | SAPED | 7.1 Digitization Strategy | Other | Administrative Compliance Tools: SAOO I-Field Equipment Tracking & Management Dashboard | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-12-29 | Complete | 0 | history
387181 | SAPED | 7.1 Digitization Strategy | Other | Administrative Compliance Tools: SAPED MOC Dashboard v1 | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-03-30 | Complete | 0 | history
387179 | SAPED | 7.1 Digitization Strategy | Other | Well Integrity Assurance: TCA Refill Tracking System (2021) | Plan | Ajmi, Fahad M | 2021-01-01 | 2021-12-31 | Complete | 0 | history
387194 | SAPED | 7.1 Digitization Strategy | Other | Well Integrity Assurance: Smart Survey Validation ( Temp Survey) | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-12-29 | Complete | 0 | history
387171 | SAPED | 7.1 Digitization Strategy | Other | Data Validity/Reliability: ICD Data Management (2021) | Plan | Ajmi, Fahad M | 2021-01-01 | 2021-09-01 | Complete | 0 | history
387199 | SAPED | 7.1 Digitization Strategy | Other | Administrative Compliance Tools: Production Engineering Data Compliance Engine Frequencies ( SWIFT) | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-12-29 | Complete | 0 | history
387176 | SAPED | 7.1 Digitization Strategy | Other | Production Optimization: Well Health Index (2021) | Plan | Ajmi, Fahad M | 2021-01-01 | 2021-12-01 | Complete | 0 | history
387198 | SAPED | 7.1 Digitization Strategy | Other | Administrative Compliance Tools: Autonomous ESP (2022) | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-12-29 | Complete | 0 | history
387177 | SAPED | 7.1 Digitization Strategy | Other | Well Integrity Assurance: Smart Survey Validation ( WHIT/ WHGR Survey) | Plan | Ajmi, Fahad M | 2021-01-01 | 2021-12-01 | Complete | 0 | history
387170 | SAPED | 7.1 Digitization Strategy | Other | Well Integrity Assurance: Synthetic Corrosion Log Phase-1 (2021) | Plan | Ajmi, Fahad M | 2021-01-01 | 2021-09-01 | Complete | 0 | history
387200 | SAPED | 7.1 Digitization Strategy | Other | Data Validity/Reliability: Advanced Real-Time Data Monitoring & Quality Assurance | Plan | Ajmi, Fahad M | 2022-01-01 | 2022-12-29 | Complete | 0 | history
387196 | SAPED | 7.1 Digitization Strategy | Other | Remote Assistance & Virtual: Smart Helmet (2022) | Plan | Ajmi, Fahad M | 2021-12-01 | 2022-12-29 | Complete | 0 | history
387167 | SAPED | 7.1 Digitization Strategy | Other | Remote Assistance & Virtual: Installing V-SAT in UDH South Admin Building (2021) | Plan | Ajmi, Fahad M | 2021-01-01 | 2021-08-01 | Complete | 0 | history
387172 | SAPED | 7.1 Digitization Strategy | Other | Administrative Compliance Tools: SWATS Authority Compliance | Plan | Ajmi, Fahad M | 2021-01-01 | 2021-11-30 | Complete | 0 | history
387175 | SAPED | 7.1 Digitization Strategy | Other | Administrative Compliance Tools: Business Value Dashboard (2021) | Plan | Ajmi, Fahad M | 2021-01-01 | 2021-12-01 | Complete | 0 | history
387165 | SAPED | 7.1 Digitization Strategy | Other | Production Optimization: ESP Failure Prediction (2021) | Plan | Ajmi, Fahad M | 2021-01-01 | 2021-05-01 | Complete | 0 | history
387174 | SAPED | 7.1 Digitization Strategy | Other | Production Optimization: MIDAS (2021) | Plan | Ajmi, Fahad M | 2021-01-01 | 2021-12-01 | Complete | 0 | history
387236 | SAPED | 7.1 Cost Efficiency Strategy | Other | Value Creation: Develop & reap benefits of CES PM | Plan | Almannai, Mohammed N | 2022-01-07 | 2022-07-25 | Complete | 0 | history
387234 | SAPED | 7.1 Cost Efficiency Strategy | Other | Value Creation: Run a Financial Survey for SAPED to identify further cost efficiency practices. | Plan | Almannai, Mohammed N | 2021-11-07 | 2022-03-09 | Complete | 0 | history
387233 | SAPED | 7.1 Cost Efficiency Strategy | Other | Cost Intelligent Hub: Run a Financial Survey for SAPED All | Plan | Almannai, Mohammed N | 2022-01-07 | 2022-03-09 | Complete | 0 | history
387231 | SAPED | 7.1 Cost Efficiency Strategy | Other | Culture Creation: Include a main competency goal for SAPED All with 10% of 2022 overall PMP goals. | Plan | Almannai, Mohammed N | 2021-11-07 | 2022-01-11 | Complete | 0 | history
387237 | SAPED | 7.1 Cost Efficiency Strategy | Other | Value Creation: Conduct Cost Benefit Analysis (CBA) for 2022 SAOO GOSPs’ | Plan | Almannai, Mohammed N | 2022-09-07 | 2022-11-09 | Complete | 0 | history
387232 | SAPED | 7.1 Cost Efficiency Strategy | Other | Value Creation: Develop and lay down the CES foundations. | Plan | Almannai, Mohammed N | 2021-11-07 | 2022-02-28 | Complete | 0 | history
387235 | SAPED | 7.1 Cost Efficiency Strategy | Other | Cost Intelligent Hub: Develop best practices for SAPED contingency jobs | Plan | Almannai, Mohammed N | 2022-02-04 | 2022-07-05 | Complete | 0 | history
387157 | SAPED | 7.1 Digitization Strategy | Other | project: WOCP Enhancement | Plan | Sultan, Abdulaziz A (SAPED) | 2020-01-01 | 2020-12-01 | Complete | 0 | history
387155 | SAPED | 7.1 Digitization Strategy | Other | Production Optimization: Well Network Modeling ( Sea Water Injection Monitoring Model ) | Plan | Sultan, Abdulaziz A (SAPED) | 2020-01-01 | 2020-12-01 | Complete | 0 | history
387164 | SAPED | 7.1 Digitization Strategy | Other | Well Integrity Assurance: Downhole leak detection | Plan | Sultan, Abdulaziz A (SAPED) | 2020-01-01 | 2020-12-31 | Complete | 0 | history
387160 | SAPED | 7.1 Digitization Strategy | Other | Production Optimization: (RICE) Acid Stimulation Candidate | Plan | Sultan, Abdulaziz A (SAPED) | 2020-01-01 | 2020-12-01 | Complete | 0 | history
387161 | SAPED | 7.1 Digitization Strategy | Other | Data Validity/Reliability: MPFM performance monitoring | Plan | Sultan, Abdulaziz A (SAPED) | 2020-01-01 | 2020-12-31 | Complete | 0 | history
387159 | SAPED | 7.1 Digitization Strategy | Other | Well Integrity Assurance: Rig less Intervention Candidate Evaluator (RICE) ( TCA Refiling) | Plan | Sultan, Abdulaziz A (SAPED) | 2020-01-01 | 2020-12-01 | Complete | 0 | history
387163 | SAPED | 7.1 Digitization Strategy | Other | Well Integrity Assurance: Rig less Intervention Candidate Evaluator (RICE) ( Annuli Integrity) | Plan | Sultan, Abdulaziz A (SAPED) | 2020-01-01 | 2020-12-31 | Complete | 0 | history
387158 | SAPED | 7.1 Digitization Strategy | Other | Production Optimization: Intelligent decision excellence application (iDeXA) | Plan | Sultan, Abdulaziz A (SAPED) | 2020-01-01 | 2020-12-01 | Complete | 0 | history
387162 | SAPED | 7.1 Digitization Strategy | Other | Well Integrity Assurance: Smart Survey Validation ( SBHP Validation) | Plan | Sultan, Abdulaziz A (SAPED) | 2020-01-01 | 2020-12-31 | Complete | 0 | history
377896 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: Tracking Dashboard - Implement prototype into OE system | Plan | Ajmi, Fahad M | 2022-08-16 | 2022-09-30 | Closed | 1 | history
377899 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: Tracking Dashboard - upload all action items for all strategies | Plan | Ajmi, Fahad M | 2022-08-16 | 2022-11-30 | Closed | 1 | history
377898 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: Tracking Dashboard - inform SAPED Strategy | Plan | Ajmi, Fahad M | 2022-08-16 | 2022-11-30 | Closed | 1 | history
387153 | SAPED | 7.1 Digitization Strategy | Other | Administrative Compliance Tools: EWAM | Plan | Sultan, Abdulaziz A (SAPED) | 2020-01-01 | 2020-05-31 | Closed | 0 | history
387154 | SAPED | 7.1 Digitization Strategy | Other | Production Optimization: Rig less Intervention Candidate Evaluator (RICE) SIS | Plan | Sultan, Abdulaziz A (SAPED) | 2020-01-01 | 2020-12-01 | Closed | 0 | history
377894 | SAPED | 7.1 Re-Branding Strategy | Self Assessment | Strategy Fulfilment: Tracking Dashboard - Finalize Tracking Formatting and prototype | Plan | Althawaiqib, Sarah A | 2022-08-16 | 2022-08-30 | Closed | 1 | history

## Highlights (hidden)
# | Strategy | Item | Date
1
2
3
4

## Notifications (hidden)
# | Strategy | Item | Date
1
2
3
4

## Overdue Actions (hidden)
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | ETC | Overdue | Completion Status
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | #REF! | #REF! | #REF! | #REF! | N/A | N/A | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | N/A | N/A | #REF! | #REF!
4 | #REF! | #REF! | #REF! | #REF! | N/A | N/A | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | N/A | N/A | #REF! | #REF!
6 | #REF! | #REF! | #REF! | #REF! | N/A | N/A | #REF! | #REF!
7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | N/A | N/A | N/A | #REF!
13 | #REF! | #REF! | #REF! | #REF! | N/A | N/A | N/A | #REF!
14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | N/A | #REF!
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | N/A | #REF!
16 | #REF! | #REF! | #REF! | #REF! | N/A | N/A | N/A | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | ETC | Overdue | Completion Status
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | N/A | #REF!
2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF! | #REF! | #REF! | N/A | N/A | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | ETC | Overdue | Completion Status
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
32 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
33 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
34 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
35 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
36 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
37 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
38 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
39 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
40 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
41 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
42 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
43 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
44 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | N/A | #REF!
45 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
46 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
47 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
48 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
49 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
50 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
51 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
52 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
53 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
54 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
55 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
56 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
57 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
58 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
59 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
60 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
61 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
62 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
63 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
64 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
65 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
66 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
67 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
68 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
69 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
70 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
71 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
72 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | ETC | Overdue | Completion Status
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | #REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | N/A | #REF!
7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | #REF! | #REF! | #REF! | #REF! | N/A | N/A | N/A | #REF!
19 | #REF! | #REF! | #REF! | #REF! | N/A | N/A | N/A | #REF!
20 | #REF! | #REF! | #REF! | #REF! | N/A | N/A | N/A | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | ETC | Overdue | Completion Status
1 | #REF! | #REF! | #REF! | #REF! | N/A | N/A | #REF! | #REF!

## Dashboard
# | Strategy | Item | Date | # | Strategy | Item | Date | #REF! | #REF! | #REF! | ETC
1 | 0 | 0 | 0 | 1 | 0 | 0 | 0
2 | 0 | 0 | 0 | 2 | 0 | 0 | 0
3 | 0 | 0 | 0 | 3 | 0 | 0 | 0
4 | 0 | 0 | 0 | 4 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dashboard
Re-Branding
Cost Efficiency
Sustainability
People Development and Engagment
Digitization
SA Production Engineering Department Strategies Tracking
Strategies
Tracking
Highlights
Overdue Actions
Notifications
Overall Status
SAPED Overall Status
Strategies Progress Status
Re-Branding
Cost Efficiency
Sustainability
People Development & Engagment
Digitalization

## Re-Branding
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | ETC | Overdue | Completion Status
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | #REF! | #REF! | #REF! | #REF! | N/A | N/A | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | N/A | N/A | #REF! | #REF!
4 | #REF! | #REF! | #REF! | #REF! | N/A | N/A | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | N/A | N/A | #REF! | #REF!
6 | #REF! | #REF! | #REF! | #REF! | N/A | N/A | #REF! | #REF!
7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1
Dashboard
Action Plan
Re-Branding
Cost Efficiency
Sustainability
People Development and Engagment
Digitization
SA Production Engineering Department Strategies Tracking
Strategies
Tracking
Sub-Strategies Progress Status
Overall Status
Strategy Fulfilment
Culture Shift Trigger
Exposure/Footprint
Re-Branding Overall Status
Timeline/Roadmap

## Cost Efficiency
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | ETC | Overdue | Completion Status
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | N/A | #REF!
2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1
Dashboard
Action Plan
Re-Branding
Cost Efficiency
Sustainability
People Development and Engagment
Digitization
SA Production Engineering Department Strategies Tracking
Strategies
Tracking
Sub-Strategies Progress Status
Overall Status
Value Creation
Cost Intelligence Hub
Culture Creation
Cost Efficiency Overall Status
Timeline/Roadmap

## Sustainability
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | ETC | Overdue | Completion Status
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1
Dashboard
Action Plan
Re-Branding
Cost Efficiency
Sustainability
People Development and Engagment
Digitization
SA Production Engineering Department Strategies Tracking
Strategies
Tracking
Sub-Strategies Progress Status
Overall Status
Environmental Stewardship
Production & Integrity
Sustainability Overall Status
Timeline/Roadmap

## People Development
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | ETC | Overdue | Completion Status
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | #REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | N/A | #REF!
7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1
Dashboard
Action Plan
Re-Branding
Cost Efficiency
Sustainability
People Development and Engagment
Digitization
SA Production Engineering Department Strategies Tracking
Strategies
Tracking
Sub-Strategies Progress Status
Overall Status
Employee Wellbeing
T&D Administration & Oversigh
Employee Performance & Engagement
People Development & Engagement Overall Status
Timeline/Roadmap

## Digitalization
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | ETC | Overdue | Completion Status
1 | #REF! | #REF! | #REF! | #REF! | N/A | N/A | #REF! | #REF!
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
Dashboard
Action Plan
Re-Branding
Cost Efficiency
Sustainability
People Development and Engagment
Digitization
SA Production Engineering Department Strategies Tracking
Strategies
Tracking
Sub-Strategies Progress Status
Overall Status
Production Optimization
Administrative Compliance Tools
Remote Assistance & Virtual
Digitalization Overall Status
Timeline/Roadmap
Data Validity/Reliability
Well Integrity Assurance
0%
0%